## Open Milestone View
Function | Primary | Status | Start | Finish | Notes (Roper 4/14) | Next Action | Owner | Priority
01. HR | Welcome to NFP - email from Doug Hammond | Complete | 2026-02-18 17:00 | 2026-02-18 17:00 | Done
01. HR | Welcome leaders to NFP and introduction of HR team and regional support | Complete | 2026-02-25 17:00 | 2026-02-25 17:00 | Done
01. HR | "Brand New Day" Welcome Meeting (March 10) | Complete | 2026-03-03 17:00 | 2026-03-03 17:00 | Done — happened 3/10
01. HR | HR Technical Training | Complete | 2026-02-24 17:00 | 2026-02-24 17:00 | Done — happened 3/3
01. HR | HR Systems/MyApplications, PeopleFirst Portal and Workplace | Complete | 2026-03-10 17:00 | 2026-03-10 17:00 | Done
01. HR | Utipro Time Management Training (employees and supervisors) | Complete | 2026-03-06 17:00 | 2026-03-06 17:00 | Done
01. HR | 1st Payroll under NFP (March 6) | Complete | 2026-03-13 17:00 | 2026-03-13 17:00 | Done — processed 3/6
01. HR | Benefits Training Session | Complete | 2026-03-25 08:00 | 2026-03-25 08:00 | Done
01. HR | Benefits Enrollment Period (March 1) | Complete | 2026-03-25 08:00 | 2026-04-14 17:00 | Enrolled 3/17
01. HR | NFP Benefits Enrollment Due | Complete | 2026-04-14 17:00 | 2026-04-14 17:00 | Enrolled
01. HR | 401(k) Employee Training Session | Complete | 2026-03-16 08:00 | 2026-03-16 08:00 | Done
01. HR | 401(k) Employee Enrollment in NFP Plan | Complete | 2026-03-16 08:00 | 2026-03-27 17:00 | Enrolled
01. HR | 401(k) Employee Transition into NFP's plan | Complete | 2026-03-27 17:00 | 2026-03-27 17:00 | Done
01. HR | NFPs Policies and Handbook | Complete | 2026-03-24 17:00 | 2026-03-24 17:00 | Reviewed in Chicago
01. HR | Compliance Training Period | Complete | 2026-04-09 08:00 | 2026-05-06 17:00 | Ninjio complete. 4/10: Broader compliance modules deferred to after July (~45-60 day window once launched)
01. HR | Compliance Training Completed | Complete | 2026-05-06 17:00 | 2026-05-06 17:00 | Done
01. HR | Concur (Travel & Expense) | Complete | 2026-03-10 17:00 | 2026-03-10 17:00 | Launched 4/2. Roper needs to learn before summit 4/13 | Learn how to book/expense | Roper | 8
01. HR | AMEX Corporate Cards | Complete | 2026-03-10 17:00 | 2026-03-10 17:00 | Received
02. Marketing | Marketing Kick-off call | Complete | 2026-02-24 17:00 | 2026-02-24 17:00 | 4/10: Complete
02. Marketing | Initial drafts of Client/employee/carrier communication templates | Complete | 2026-03-03 17:00 | 2026-03-03 17:00 | 4/10: Complete
02. Marketing | Define client communication / letters | In Progress | 2026-03-10 17:00 | 2026-03-10 17:00 | 4/10: Email preferred over printed letters. Draft client email + press release to be shared for review | Review draft email + press release when shared | Roper (waiting on Alma Ko)
02. Marketing | Client communication period | In Progress | 2026-03-11 08:00 | 2026-04-07 17:00 | Ends 4/7 per dashboard |  | Alma Ko
02. Marketing | Finalize client communication |  | 2026-04-07 17:00 | 2026-04-07 17:00
02. Marketing | PR Cyber Security Environment Validation (from IT/IMO) | Complete | 2026-03-19 17:00 | 2026-03-19 17:00 | Done — Roper DIY + Umzuzu
02. Marketing | PR Precautionary message to employees |  | 2026-04-15 17:00 | 2026-04-15 17:00
02. Marketing | "Go-Green" (rebranding to NFP - TBC) |  | 2026-06-02 17:00 | 2026-06-02 17:00 | 4/10: Timing aligned with tech milestones (email migration, Day-in-Life sessions). Go Green date proposed after IT assessment
02. Marketing | Business Cards |  | 2026-06-03 17:00 | 2026-06-03 17:00
02. Marketing | Collateral materials |  | 2026-06-03 17:00 | 2026-06-03 17:00
02. Marketing | Website Transition |  | 2026-06-03 17:00 | 2026-06-03 17:00 | 4/10: Minimal collateral to transition; expected to be light
02. Marketing | Transition Social media |  | 2026-06-03 17:00 | 2026-06-03 17:00
02. Marketing | Signage |  | 2026-06-03 17:00 | 2026-06-03 17:00
03. Technology | @NFP email addresses creation | Complete | 2026-03-10 17:00 | 2026-03-10 17:00 | Done. Need to disable @SignatureAdvisor forwarding | Disable forwarding | Roper | 4
03. Technology | Adjustments on legacy email system to avoid spam | Complete | 2026-02-20 17:00 | 2026-02-20 17:00 | Done
03. Technology | Technology Intro call with acquisition IT team | Complete | 2026-02-24 17:00 | 2026-02-24 17:00 | Done
03. Technology | Cybersecurity Environment Assessment / Security Scan | Complete | 2026-02-24 17:00 | 2026-02-24 17:00 | Done
03. Technology | Cybersecurity Environment Remediation (if needed) | Complete | 2026-03-26 17:00 | 2026-03-26 17:00 | Done — Roper DIY + Umzuzu. 4/10: Largely complete; remaining item is CrowdStrike Mac agent (pending Aon delivery)
03. Technology | Ninjio Launch | Complete | 2026-03-11 17:00 | 2026-03-11 17:00 | Done
03. Technology | Ninjio Training Period | Complete | 2026-03-12 08:00 | 2026-04-08 17:00 | Done
03. Technology | Ninjio Training Completed | Complete | 2026-04-08 17:00 | 2026-04-08 17:00 | Done
03. Technology | Email System Migration (TBC) |  | 2026-06-02 17:00 | 2026-06-02 17:00
03. Technology | Email domain change to @nfp.com (TBC) |  | 2026-06-02 17:00 | 2026-06-02 17:00
03. Technology | Email Migration Hypercare |  | 2026-06-03 08:00 | 2026-06-09 17:00
03. Technology | Conduct Office Integration (TBC) |  | 2026-06-02 17:00 | 2026-06-02 17:00
03. Technology | Hypercare |  | 2026-06-03 08:00 | 2026-06-09 17:00
03. Technology | Post-IT Integration Training (Acadame) |  | 2026-06-10 08:00 | 2026-06-16 17:00
03. Technology | Phone Migration | Complete | 2026-06-02 17:00 | 2026-06-02 17:00 | RingCentral live. Old carrier canceled. Fax deprecated
03. Technology | "Day in the life" sessions | In Progress | 2026-04-06 08:00 | 2026-04-17 17:00 | Initial session 3/28 done. 3 follow-ups requested. 4/10: Still outstanding; team will coordinate scheduling based on availability | Scheduling with Roper | Roper (waiting) | 15
03. Technology | ⬅️ Application Deep Dive — Airtable | Not Started |  |  | ⬅️ NEW 4/6 — Courtney Kendrick requested 4/2, follow-up 4/6. Target week of 4/13. ~1 hour | Provide availability | Roper (waiting) | 15
03. Technology | ⬅️ Application Deep Dive — Claude AI | Not Started |  |  | ⬅️ NEW 4/6 — Courtney Kendrick requested 4/2, follow-up 4/6. Target week of 4/20. ~1 hour | Provide availability | Roper (waiting) | 15
04. Finance | Workday Company (GL) Creation | Complete | 2026-02-24 17:00 | 2026-02-24 17:00 | Done
04. Finance | GL Mapping | Complete | 2026-03-03 17:00 | 2026-03-03 17:00 | Done
04. Finance | Closing balance sheet review and upload | In Progress | 2026-03-10 17:00 | 2026-03-10 17:00 | OVERDUE — Roper needs to undo 2/17 QB reconciliation. 4/10: March close required estimates due to missing financials; access/docs still needed from Roper | Undo reconciliation in QB: Acct 1003 > History > Undo | Roper | 2
04. Finance | Month end and finance & accounting processes onboarding | In Progress | 2026-03-04 08:00 | 2026-04-14 17:00 | March close in progress |  | Mary Bamford
04. Finance | Upload month 1 closing activity | In Progress | 2026-03-25 17:00 | 2026-03-25 17:00 | Blocked by QB reconciliation undo. 4/10: March close used estimates due to missing financials |  | Roper → Mary Bamford
04. Finance | Upload month 2 closing activity |  | 2026-04-22 17:00 | 2026-04-22 17:00
04. Finance | Coupa/ Accounts Payable Onboarding | Not Started | 2026-04-21 17:00 | 2026-04-21 17:00 | 4/10: Roper to share list of active suppliers with Logan. Working session or admin access next step | Review QB vendors for Coupa | Roper | 7
04. Finance | Opening balance sheet & working capital true-up calculation |  | 2026-06-02 17:00 | 2026-06-02 17:00
04. Finance | ⬅️ AmEx statement — 3/20 payment for Mary Bamford | Not Started |  |  | ⬅️ NEW 4/6 — Mary asked 4/6. Needs for March close (hard deadline today) | Locate and send AmEx statement to Mary | Roper | 2
04. Finance | ⬅️ Expense descriptions — Acumen KS $1,250 + OgleTree Deakins $170.10 | Not Started |  |  | ⬅️ NEW 4/6 — Mary asked 4/6. Invoices or statements needed | Provide descriptions + supporting docs to Mary | Roper | 2
04. Finance | ⬅️ Deposit support — carrier statements for March | Not Started |  |  | ⬅️ NEW 4/6 — Mary asked 4/6. Less critical, by tomorrow | Email carrier statements to Mary | Roper | 6
05. Treasury | Banking Assessment | Complete | 2026-03-03 17:00 | 2026-03-03 17:00 | Done
05. Treasury | Creation of Wells Fargo Accounts (if needed) | Complete | 2026-03-24 17:00 | 2026-03-24 17:00 | Not needed per Keara recap
05. Treasury | Closing selected legacy bank accounts |  | 2026-03-10 17:00 | 2026-03-10 17:00 | 4/10: One legacy account remains; will be closed as Wells Fargo transition progresses
05. Treasury | Addition of NFP signatory representative on legacy account (if applicable) | Complete | 2026-05-19 17:00 | 2026-05-19 17:00 | Signers added to Landmark
05. Treasury | Migration to Wells Fargo / NFP Banking Platform (TBC) |  | 2026-05-26 17:00 | 2026-05-26 17:00
07. Risk Management | Addition of coverage under NFP/Aon Insurance Program | Complete | 2026-02-17 17:00 | 2026-02-17 17:00 | Done
07. Risk Management | Procurement of ERP's for E&O | Complete | 2026-02-17 17:00 | 2026-02-17 17:00 | Paid KAIA, endorsement received
08. Carrier Management | SIA communication with local contacts | Complete | 2026-02-19 17:00 | 2026-02-19 17:00 | Done
08. Carrier Management | Initial Market Notification to NFP Contacts | Complete | 2026-03-03 17:00 | 2026-03-03 17:00 | Sam Brown sent initial announcement
08. Carrier Management | Full Market Notification Initiation | In Progress | 2026-04-14 17:00 | 2026-04-14 17:00 | Sam Brown Step 2. 4/10: Nolan assisting Sam. Downloads timing depends on code updates to NFP. Sam following up internally | Reply with address, phone, fax, contact roles, emails | Roper | 9
08. Carrier Management | Ongoing Market Notification and consolidation |  | 2026-04-15 08:00 | 2026-05-12 17:00
09. Licensing & Registrations | Change of Registered Agent to CT Corp. (Secretary of State) | Complete | 2026-03-03 17:00 | 2026-03-03 17:00 | Done
09. Licensing & Registrations | Introduction to Insurance Licensing | Complete | 2026-03-31 17:00 | 2026-03-31 17:00 | Lisa Black handling via RegEd
09. Licensing & Registrations | Initiation or Reged Process | In Progress | 2026-04-14 17:00 | 2026-04-14 17:00 | Personal licenses in RegEd. 4/10: Tess pursuing MA P&C (expects month-end). Entity licenses stay active while policies in force, phase out through renewal cycle. Lisa to connect Roper with legal re: operational support for entity license renewals | Connect with Lisa + legal re: entity license renewals | Roper | 14
10. Region/Sales/Ops | Regional Sales Updates |  | 2026-04-22 08:00 | 2026-05-19 17:00
ROPER'S ADDITIONAL ITEMS (added 4/5)
Integration | Send ranked list to Keara | In Progress | 2026-04-05 |  | This spreadsheet | Send to Keara | Roper | 1
Regional/Sales | Tess full-time conversation with Brett | Not Started | 2026-04-05 |  | Tess pursuing MA P&C license (NFP reimburses). 4/10: Expects to complete testing by month-end | Schedule conversation with Brett | Roper | 3
Technology | AI Strategy deep dive + Gaya pilot | Not Started | 2026-04-05 |  | Mark Rieder + Katherine Minami | Confirm Mon 4/6 3pm CT invite | Roper | 5
Technology | CanopyConnect credentials | Not Started | 2026-04-05 |  | Demo done with Josh Zacher | Get user ID and password | Josh Zacher → Roper | 10
Regional/Sales | Goals in UltiPro | Not Started | 2026-04-05 |  | PCG retention 93.5%, PR retention 90%, growth 5.3% | Enter goals in UltiPro | Roper | 12
Regional/Sales | NB premium goal for EPIC | Not Started | 2026-04-05 |  | Mary Mullen asked 2/26 | Clarify what Mary needs, provide goal | Roper | 13
Technology | DNS/Registrar migration + domain admin | Not Started | 2026-04-05 |  | John Seckner: Hover to Brandsight. Tracy needs admin ¦ Courtney follow-up 4/6: John needs DNS exports (Excel) for 4 domains this week | Export DNS records (Excel), give admin access | Roper (waiting) | 16
Regional/Sales | Life insurance policy list + commission | Not Started | 2026-04-05 |  | Julie Lovall + Logan Christianson | Provide active life policy list | Roper (waiting) | 17
Carrier Mgmt | Berkley One code decision | Not Started | 2026-04-05 |  | Roper prefers dedicated KC code. Not urgent | Decide when Mary raises it | Roper (waiting) | 18
Technology | Copilot license | Not Started | 2026-04-05 |  | ServiceNow REQ0412467 | Sign consent form, activate | Roper | 19
Regional/Sales | P&C Town Hall — April 20 | Not Started | 2026-04-05 |  | Registration open | Register | Roper | 19
WAITING ON NFP (added 4/5)
Regional/Sales | Susan Clifford — ALT report / AI agent | Waiting |  |  | Susan owes Roper sample data | Send sample data | Susan Clifford
HR | HSA accounts (Optum) | Waiting |  |  | Andria Griffin to open accounts | Open Optum accounts, address on 4/6 paycheck | Andria Griffin
Technology | Epic smoke testing + go-live | Waiting |  |  | 4/10: Phase 1 complete. Phase 2 partially complete (Workday reversal mapping issue being corrected). Branch expected live soon after | Complete smoke testing | NFP Tech
Marketing | Go-Green rebranding | Waiting |  |  | Target ~June |  | NFP Marketing
Marketing | Business cards + collateral + signage | Waiting |  |  | Target ~June |  | NFP Marketing
Marketing | Website transition | Waiting |  |  | Target ~June |  | NFP Marketing
Marketing | Social media transition | Waiting |  |  | Target ~June |  | NFP Marketing
Technology | Email system migration to @nfp.com | Waiting |  |  | Full migration + hypercare, target ~June |  | NFP Tech
Technology | Office integration (conduct) | Waiting |  |  | Target ~June |  | NFP Tech
COLOR LEGEND
Dark Green | Keara's item — confirmed complete
Yellow | Keara's item — Roper updated with notes/status
Blue | Roper added — not in Keara's original
No color | Keara's original — no update from Roper

## Comments
Row 24 | Good afternoon, all: We’re excited to advance our evolution and take advantage of the momentum we’ve created due to our partnership with NFP and will issue a public press release announcing the deal on 10/12/2023. We wanted to take this opportunity to make you aware there's building evidence across the cybersecurity community that bad actors may use press releases announcing mergers and acquisitions as a trigger to go after companies with cyber-attacks, including phishing, malware or ransomware. Nothing has changed relating to our processes and workflows, so please continue to follow our standard operating procedures. No one will reach out to you and ask for your passwords or unexpectedly request employee or client information. If you receive any requests that seem even remotely suspect, we ask that you check with leadership before completing the request. In closing, be especially vigilant now and in the coming weeks and continue to adhere to our IT and Cybersecurity polices. Thank you, XXXXX | Marco Altamirano Leiva | 11/20/23 12:59 PM