## Open Milestone View
Function | Primary | Status | Start | Finish | Notes (Roper 4/26) | Next Action | Owner | Owner Basis | Owner Confidence | Problem Type | Priority | Baseline Row | Status Change (4/14→4/26)
01. HR | Welcome to NFP - email from Doug Hammond | Complete | 2026-02-18 16:59:59.999000 | 2026-02-18 16:59:59.999000 | Doug Hammond welcome email landed 2/18 confirming SPI is officially on the NFP family roster. Foundational kickoff communication; no further action. | (close as resolved) | Doug Hammond | explicit | high | Resolved |  | 2
01. HR | Welcome leaders to NFP and introduction of HR team and regional support | Complete | 2026-02-25 16:59:59.999000 | 2026-02-25 16:59:59.999000 | HR team and regional support introductions completed via Stephanie Goldman handoff [email#386, email#1317, email#1318] and reinforced across bi-weekly integration reviews [email#102, email#150, email#194]. Mary Mullen and Jackie Searles surfaced as ongoing operating contacts. Monthly HR status meeting now standing [cal#1573]. | (close as resolved) | Stephanie Goldman | explicit | high | Resolved |  | 3
01. HR | "Brand New Day" Welcome Meeting (March 10) | Complete | 2026-03-03 16:59:59.999000 | 2026-03-03 16:59:59.999000 | Brand New Day welcome session held 3/10 as planned per baseline tracker. | (close as resolved) | NFP HR (corporate) | mentioned | medium | Resolved |  | 4
01. HR | HR Technical Training | Complete | 2026-02-24 16:59:59.999000 | 2026-02-24 16:59:59.999000 | HR technical training delivered 3/3 with Mary Mullen as central coordinator [email#16, email#17, email#18, email#24, email#25]. Reinforced in subsequent leader sessions [email#470, email#473-475, email#1515-1519]. | (close as resolved) | Mary Mullen | implied | medium | Resolved |  | 5
01. HR | HR Systems/MyApplications, PeopleFirst Portal and Workplace | Complete | 2026-03-10 16:59:59.999000 | 2026-03-10 16:59:59.999000 | PeopleFirst Portal and MyApplications walkthroughs delivered with Nancy Cronin support [email#1227, email#1228, email#1231, email#1232, email#1513]. Reinforced through ongoing HR comms [email#1303, email#1316]. | (close as resolved) | Nancy Cronin | implied | medium | Resolved |  | 6
01. HR | Utipro Time Management Training (employees and supervisors) | Complete | 2026-03-06 16:59:59.999000 | 2026-03-06 16:59:59.999000 | UltiPro Time Management training closed per baseline; PTO cutover sequencing now folded into Workday HCM go-live tracker [transcript#351]. | (close as resolved) | Mary Mullen | implied | medium | Resolved |  | 7
01. HR | 1st Payroll under NFP (March 6) | Complete | 2026-03-13 16:59:59.999000 | 2026-03-13 16:59:59.999000 | First NFP payroll processed 3/6 with Kellie Green driving from the payroll side [email#74, email#75, email#76, email#78, email#1178]. Andria Griffin manually applied 3/20 benefit deductions including missed 3/6 premiums [email#1057, email#1061]. | (close as resolved) | Kellie Green | explicit | high | Resolved |  | 8
01. HR | Benefits Training Session | Complete | 2026-03-25 08:00:00 | 2026-03-25 08:00:00 | Benefits training delivered through Kim Pillar's session series [email#374-378, email#380, email#383, email#464-477]. Marked complete per baseline. | (close as resolved) | Kim Pillar | implied | medium | Resolved |  | 9
01. HR | Benefits Enrollment Period (March 1) | Complete | 2026-03-25 08:00:00 | 2026-04-14 16:59:59.999000 | Benefits enrollment closed 3/17 with Andria Griffin operating ground truth [email#889, email#890, email#899, email#928, email#929, email#1093]. Jackie Searles supported on the HRIS/onboarding side [email#93, email#96, email#104]. HSA accounts (Optum) still not opened — split out as separate stuck milestone (row 95). | (close as resolved) | Andria Griffin | explicit | high | Resolved |  | 10
01. HR | NFP Benefits Enrollment Due | Complete | 2026-04-14 16:59:59.999000 | 2026-04-14 16:59:59.999000 | Enrollment deadline met; Andria Griffin confirmed completion and applied premium catch-up to 3/20 paycheck [email#1061]. | (close as resolved) | Andria Griffin | implied | medium | Resolved |  | 11
01. HR | 401(k) Employee Training Session | Complete | 2026-03-16 08:00:00 | 2026-03-16 08:00:00 | 401(k) employee training session delivered per baseline. | (close as resolved) | Kim Pillar | implied | medium | Resolved |  | 12
01. HR | 401(k) Employee Enrollment in NFP Plan | Complete | 2026-03-16 08:00:00 | 2026-03-27 16:59:59.999000 | 401(k) enrollment completed via Jackie Searles' onboarding pipeline [email#93, email#96, email#100, email#104]. | (close as resolved) | Jackie Searles | explicit | high | Resolved |  | 13
01. HR | 401(k) Employee Transition into NFP's plan | Complete | 2026-03-27 16:59:59.999000 | 2026-03-27 16:59:59.999000 | 401(k) transition closed per baseline; legacy plan rollover paths communicated. | (close as resolved) | NFP HR (corporate) | mentioned | medium | Resolved |  | 14
01. HR | NFPs Policies and Handbook | Complete | 2026-03-24 16:59:59.999000 | 2026-03-24 16:59:59.999000 | Handbook reviewed in Chicago session per baseline. Jackie Searles confirmed acknowledgements via HRIS template completion [email#101, email#234, email#235, email#236]. Nancy Cronin supported policy questions [email#559, email#594]. | (close as resolved) | Jackie Searles | explicit | high | Resolved |  | 15
01. HR | Compliance Training Period | Complete | 2026-04-09 08:00:00 | 2026-05-06 16:59:59.999000 | Ninjio core complete per baseline; broader compliance modules deferred to post-July 45-60 day window [email#551, email#828, email#829]. | (close as resolved) | NFP Compliance (corporate) | mentioned | medium | Resolved |  | 16
01. HR | Compliance Training Completed | Complete | 2026-05-06 16:59:59.999000 | 2026-05-06 16:59:59.999000 | Compliance training completed per baseline tracker. | (close as resolved) | NFP Compliance (corporate) | mentioned | medium | Resolved |  | 17
01. HR | Concur (Travel & Expense) | Complete | 2026-03-10 16:59:59.999000 | 2026-03-10 16:59:59.999000 | Concur launched 4/2; Roper learned the booking/expense flow before 4/13 NFP Personal Risk Summit [email#155, email#334]. Note: separate 'Concur T&E onboarding for Roper specifically' tracked in Finance for ownership-vacuum risk. | (close as resolved) | Roper | explicit | high | Resolved | 8 | 18
01. HR | AMEX Corporate Cards | Complete | 2026-03-10 16:59:59.999000 | 2026-03-10 16:59:59.999000 | AmEx corporate cards received per baseline. Jackie Searles closed loop on issuance [email#96, email#97, email#112, email#113]. (Bamford 3/20 payment exception tracked separately under Finance.) | (close as resolved) | Jackie Searles | explicit | high | Resolved |  | 19
01. HR | HSA accounts (Optum) | Stuck |  |  | Optum HSA accounts still not opened as of 4/26 — weeks past the original baseline. Andria Griffin flagged the missing accounts on 3/17 and committed to address premiums on the 4/6 paycheck [email#1061, email#1057], but no Optum open-confirmation has surfaced. Blocks pre-tax HSA contributions for Roper & Crystal. | Andria Griffin to confirm Optum account creation and back-true HSA contributions; escalate to Mary Mullen if not resolved this week. | Andria Griffin | explicit | high | Ownership Vacuum |  | 95 | Waiting → Stuck
01. HR | HRIS Employee Tracker / I-9 / Onboarding Template completion | Complete |  |  | Jackie Searles delivered the HR import template and Employee Tracker pre-close [email#410] and walked the SPI roster through PeopleFirst onboarding [email#418, email#427]. I-9s, demographics, and onboarding template were submitted on schedule [email#437, email#1312]. Foundation for all downstream HRIS, payroll, and benefits enrollment. | (close as resolved) | Jackie Searles | explicit | high | Resolved |  |  | NEW (not in 4/14 baseline)
01. HR | Vendor onboarding into Aon Coupa supplier system | Open |  |  | Cross-function HR/Finance: NFP Procurement (via Coupa) requested SPI vendor list to onboard business-related expense vendors [email#117]. No NFP delivery owner has been named on the SPI side; Roper was asked to drive the data pull. Tracks alongside the Finance Coupa/AP onboarding milestone but the supplier-list piece sits with HR/operations. | Name an NFP-side owner for the SPI supplier intake; route to existing Finance Coupa/AP workstream. | unassigned | unassigned | low | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
01. HR | UltiPro 2026 goals setup meetings (Mary Mullen) | Open |  |  | Mary Mullen scheduled 1:1 goals meetings for the SPI leaders [email#1167, cal#1523] and walked Roper through the UltiPro Myself/Goals workflow [email#1085, email#1087]. Goal entry has begun but full SMART population across the 5 categories is in flight. See MEMORY ultipro-goals (10/20/30 Central Region targets drafted). | Roper to finalize UltiPro SMART goals across all 5 categories before next 1:1 with Mary. | Mary Mullen | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
01. HR | Laptop / hardware provisioning for SPI team | Open |  |  | Julie Lovall (SVP National Operations) opened the laptop provisioning thread on 2/19 asking platform [email#416]. Hardware request is owned cleanly by Julie but no completion confirmation in the corpus; treat as in-flight until SPI team standard-issue laptops land or an exception is documented. | Confirm laptop fulfillment status with Julie Lovall; close once SPI team is on NFP-issued hardware. | Julie Lovall | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
01. HR | Workday HCM Go-Live June 29 | Open |  |  | Corporate-wide Workday HCM go-live scheduled June 29 [email#193]. Central Region team meeting 4/23 confirmed cutover testing in progress and PTO transition implications [transcript#352]. Major HRIS migration off UltiPro/PeopleFirst — sequencing dependency for goals, payroll, benefits going forward. | Track NFP HR communications for SPI-specific cutover tasks; confirm PTO balance carryover plan before 6/29. | NFP HR (corporate) | mentioned | medium | Sequencing |  |  | NEW (not in 4/14 baseline)
02. Marketing | Marketing Kick-off call | Complete | 2026-02-24 16:59:59.999000 | 2026-02-24 16:59:59.999000 | 4/10: Complete [apr26] [src#335 2026-04-10 NFP marketing intro call with Alba and Robyn]; [src#56 2026-02-27 Summary, notes & next steps for: "🗽NFP - Bi-Weekly Integrati]; [src#1311 2026-02-27 RE: Signature <> NFP-Marketing Intro] |  | Marco Altamirano | explicit (evidence) | high | Resolved |  | 20
02. Marketing | Initial drafts of Client/employee/carrier communication templates | Complete | 2026-03-03 16:59:59.999000 | 2026-03-03 16:59:59.999000 | 4/10: Complete |  |  | unknown | low | Resolved |  | 21
02. Marketing | Define client communication / letters | Stuck | 2026-03-10 16:59:59.999000 | 2026-03-10 16:59:59.999000 | 4/10: Email preferred over printed letters. Draft client email + press release to be shared for review [apr26] [src#515 2026-04-21 RE: For Review: Signature Personal Ins. Press Release & Clie]; [src#275 2026-04-21 Re: Fw: Join Us! NFP P&C Executive Education Series - April ]; [src#518 2026-04-21 RE: For Review: Signature Personal Ins. Press Release & Clie] | Send Roper-side legal/E&O risk callouts to Alma + request Brett alignment before client send | Roper | explicit (evidence) | high | Active |  | 22 | In Progress → Stuck
02. Marketing | Client communication period | In Progress | 2026-03-11 08:00:00 | 2026-04-07 16:59:59.999000 | Ends 4/7 per dashboard |  | Alma Ko | baseline | medium | Sequencing |  | 23
02. Marketing | Finalize client communication | Waiting | 2026-04-07 16:59:59.999000 | 2026-04-07 16:59:59.999000 |  | Hold for NFP June cutover sequencing |  | unknown | low | Sequencing |  | 24
02. Marketing | PR Cyber Security Environment Validation (from IT/IMO) | Complete | 2026-03-19 16:59:59.999000 | 2026-03-19 16:59:59.999000 | Done — Roper DIY + Umzuzu |  |  | unknown | low | Resolved |  | 25
02. Marketing | PR Precautionary message to employees | Waiting | 2026-04-15 16:59:59.999000 | 2026-04-15 16:59:59.999000 |  | Hold for NFP June cutover sequencing |  | unknown | low | Sequencing |  | 26
02. Marketing | "Go-Green" (rebranding to NFP - TBC) | Waiting | 2026-06-02 16:59:59.999000 | 2026-06-02 16:59:59.999000 | 4/10: Timing aligned with tech milestones (email migration, Day-in-Life sessions). Go Green date proposed after IT assessment | Hold for NFP June cutover sequencing |  | unknown | low | Sequencing |  | 27
02. Marketing | Business Cards | Waiting | 2026-06-03 16:59:59.999000 | 2026-06-03 16:59:59.999000 |  | Hold for NFP June cutover sequencing |  | unknown | low | Sequencing |  | 28
02. Marketing | Collateral materials | Complete | 2026-06-03 16:59:59.999000 | 2026-06-03 16:59:59.999000 | [apr26] [src#953 2026-03-25 *NEW* Yacht Practice Collateral]; [src#1182 2026-03-06 New Marketing Piece] |  | Susan Clifford | explicit (evidence) | high | Resolved |  | 29
02. Marketing | Website Transition | Waiting | 2026-06-03 16:59:59.999000 | 2026-06-03 16:59:59.999000 | 4/10: Minimal collateral to transition; expected to be light | Hold for NFP June cutover sequencing |  | unknown | low | Sequencing |  | 30
02. Marketing | Transition Social media | Waiting | 2026-06-03 16:59:59.999000 | 2026-06-03 16:59:59.999000 | [apr26] [src#1236 2026-03-02 NFP Corp Daily Digest] | Hold for NFP June cutover sequencing |  | baseline | low | Sequencing |  | 31
02. Marketing | Signage | Waiting | 2026-06-03 16:59:59.999000 | 2026-06-03 16:59:59.999000 |  | Hold for NFP June cutover sequencing |  | unknown | low | Sequencing |  | 32
02. Marketing | Go-Green rebranding | Waiting |  |  | Target ~June | Hold for NFP June cutover sequencing | NFP Marketing | baseline | medium | Sequencing |  | 97
02. Marketing | Business cards + collateral + signage | Waiting |  |  | Target ~June | Hold for NFP June cutover sequencing | NFP Marketing | baseline | medium | Sequencing |  | 98
02. Marketing | Website transition | Waiting |  |  | Target ~June | Hold for NFP June cutover sequencing | NFP Marketing | baseline | medium | Sequencing |  | 99
02. Marketing | Social media transition | Waiting |  |  | Target ~June | Hold for NFP June cutover sequencing | NFP Marketing | baseline | medium | Sequencing |  | 100
02. Marketing | PCG Confidential Client coding -- recurring report flagging Signature clients at risk of Corp P&C marketing contact | In Progress |  |  | Recurring NFP report. Without flag, Signature clients are visible to non-Personal-Risk staff and pulled into Corp P&C marketing campaigns. Susan delivers; Roper/Crystal action. [apr26] [src#1466 2026-04-22 PCG Confidential Client]; [src#956 2026-03-25 PCG Confidential Client] | Each cycle: review Susan's report, set 'PCG Confidential Client' flag at account level for any unflagged Signature clients | Susan Clifford | explicit (evidence) | high | Active |  |  | NEW (not in 4/14 baseline)
02. Marketing | Pause domain/DNS migration; align Mary, Marco, Brett before resuming marketing/IT migration work | In Progress |  |  | Roper-paused 4/23 (src#1446). Cross-function with Tech. Domains are not client-facing -- no time sensitivity. Pause is precondition for downstream marketing+IT work. [apr26] [src#1446 2026-04-23 RE: Weekly 1:1: picking a standing slot] | Keara confirms pause to John; Roper to attend Keara/Mary/Marco alignment call; resume only after integration path is agreed | Roper | explicit (evidence) | high | Active |  |  | NEW (not in 4/14 baseline)
03. Technology | @NFP email addresses creation | Complete | 2026-03-10 16:59:59.999000 | 2026-03-10 16:59:59.999000 | Closed in baseline. | None. | Roper | explicit | high | Active | 4 | 33
03. Technology | Adjustments on legacy email system to avoid spam | Complete | 2026-02-20 16:59:59.999000 | 2026-02-20 16:59:59.999000 | Closed in baseline. | None. | NFP Tech | mentioned | low | Active |  | 34
03. Technology | Technology Intro call with acquisition IT team | Complete | 2026-02-24 16:59:59.999000 | 2026-02-24 16:59:59.999000 | Closed at intro call (src 386). | None. | Marco Alta (NFP) | explicit | high | Active |  | 35
03. Technology | Cybersecurity Environment Assessment / Security Scan | Complete | 2026-02-24 16:59:59.999000 | 2026-02-24 16:59:59.999000 | NFP IT delivery model worked cleanly — Brandon Jackson + Tracy McClain owned scan + credentials handoff end-to-end (src 89, 414, 415, 420, 424, 805). | None — closed. | Brandon Jackson + Tracy McClain (NFP) | explicit | high | Active |  | 36
03. Technology | Cybersecurity Environment Remediation (FortiClient + Ninjio) | In Progress | 2026-03-26 16:59:59.999000 | 2026-03-26 16:59:59.999000 | FortiClient rollout 04/22 (src 506, 543); Ninjio episode delivered 04/20 (src 551); ongoing remediation cadence (src 660). | Confirm FortiClient install on Roper's machine; finish Ninjio episode. | NFP Tech (FortiClient: NFP Tech Ops) | explicit | high | Active |  | 37 | Complete → In Progress
03. Technology | Ninjio Launch | Complete | 2026-03-11 16:59:59.999000 | 2026-03-11 16:59:59.999000 | Closed in baseline. | None. | NFP Tech | mentioned | low | Active |  | 38
03. Technology | Ninjio Training Period | Complete | 2026-03-12 08:00:00 | 2026-04-08 16:59:59.999000 | Closed in baseline; ongoing episodes (src 551). | None. | Roper | mentioned | low | Active |  | 39
03. Technology | Ninjio Training Completed | Complete | 2026-04-08 16:59:59.999000 | 2026-04-08 16:59:59.999000 | Closed in baseline. | None. | Roper | mentioned | low | Active |  | 40
03. Technology | Email System Migration (TBC) | Not Started | 2026-06-02 16:59:59.999000 | 2026-06-02 16:59:59.999000 | TBC; sequenced after DNS. | Hold. | NFP Tech | mentioned | low | Sequencing |  | 41
03. Technology | Email domain change to @nfp.com (TBC) | Not Started | 2026-06-02 16:59:59.999000 | 2026-06-02 16:59:59.999000 | TBC. | Hold. | NFP Tech | mentioned | low | Sequencing |  | 42
03. Technology | Email Migration Hypercare | Not Started | 2026-06-03 08:00:00 | 2026-06-09 16:59:59.999000 | TBC. | Hold. | NFP Tech | mentioned | low | Sequencing |  | 43
03. Technology | Conduct Office Integration (TBC) | Not Started | 2026-06-02 16:59:59.999000 | 2026-06-02 16:59:59.999000 | TBC. | Hold. | NFP Tech | mentioned | low | Sequencing |  | 44
03. Technology | Hypercare | Not Started | 2026-06-03 08:00:00 | 2026-06-09 16:59:59.999000 | TBC. | Hold. | NFP Tech | mentioned | low | Sequencing |  | 45
03. Technology | Post-IT Integration Training (Acadame) | Not Started | 2026-06-10 08:00:00 | 2026-06-16 16:59:59.999000 | TBC. | Hold. | NFP Tech | mentioned | low | Active |  | 46
03. Technology | Phone Migration | Complete | 2026-06-02 16:59:59.999000 | 2026-06-02 16:59:59.999000 | Closed in baseline. | None. | NFP Tech | mentioned | low | Active |  | 47
03. Technology | "Day in the life" sessions | In Progress | 2026-04-06 08:00:00 | 2026-04-17 16:59:59.999000 | Keith Clemons blocked Tue 04/21 11am Teams session w/ recording (src 652). Day-in-the-life follow-up Airtable deep dive logged 04/21 (src 349). | Complete recorded session; share artifacts. | Roper / Keith Clemons (NFP) | explicit | high | Active | 15 | 48
03. Technology | Application Deep Dive — Airtable | In Progress |  |  | Day-in-the-life follow-up scheduled, Airtable deep dive on agenda (src 349, 652). | Hold scheduled deep-dive session w/ Courtney. | Roper / Courtney Kendrick | explicit | high | Active | 15 | 49 | Not Started → In Progress
03. Technology | Application Deep Dive — Claude AI | Not Started |  |  | Claude AI deep-dive deferred behind Epic + DNS workstreams; not blocked, queued by Roper. | Schedule once Epic hypercare stabilizes. | Roper (waiting) | explicit | medium | Sequencing | 15 | 50
03. Technology | AI Strategy deep dive + Gaya pilot | In Progress | 2026-04-05 00:00:00 |  | AI strategy + technology roadmap discussed on 04/01 NFP team meeting (src 356). | Schedule Gaya pilot scoping with Rieder/Minami. | Mark Rieder / Katherine Minami / Roper | explicit | high | Active | 5 | 82 | Not Started → In Progress
03. Technology | CanopyConnect credentials | In Progress | 2026-04-05 00:00:00 |  | Discovery covered on 03/27 NFP team meeting; Roper noted pricing favorable (src 341). | Receive credentials from Josh Zacher. | Josh Zacher → Roper | explicit | high | Active | 10 | 83 | Not Started → In Progress
03. Technology | DNS/Registrar migration + domain admin | In Progress | 2026-04-05 00:00:00 |  | Roper paused 04/23 due to email-outage risk during client work crunch (src 494, 511, 520, 593). Right call — staged async work continues; TrustSPI / SignatureAdviser / SignatureAdvisor.com queued for export. NOT an Ownership Vacuum — clear owner, deliberate timing. | Send DNS export to Seckner async; revisit standing 1:1 post-Epic. | John Seckner (NFP) / Roper | explicit | high | Sequencing | 16 | 86 | Not Started → In Progress
03. Technology | Copilot license | Not Started | 2026-04-05 00:00:00 |  | No new evidence this cycle. | Request license at next NFP IT touchpoint. | Roper | explicit | medium | Active | 19 | 89
03. Technology | Epic smoke testing + go-live (KC1 branch) | In Progress |  |  | KC1 branch live 04/16 BUT downloads NOT enabled — manual workflow only (src 615). Activity & Policy Type codes tied to Sam Brown / Nolan, blocking automation (src 586). Training in flight (src 346, 347, 348). Smoke test conducted (src 307); ongoing PTO/cutover sequencing (src 351). Genuine sequencing blocker, not ownership vacuum. | Push Carrier Mgmt for codes-tied resolution; enable downloads on KC1. | NFP Tech (Mary Ondrasek, Jane Harlow, Julie Lovall) + Roper | explicit | high | Sequencing |  | 96 | Waiting → In Progress
03. Technology | Email system migration to @nfp.com | Waiting |  |  | Sequenced behind DNS migration pause and Epic hypercare. | Reactivate after DNS export delivered to Seckner. | NFP Tech | mentioned | medium | Sequencing |  | 101
03. Technology | Office integration (conduct) | Waiting |  |  | Sequenced w/ email migration. | Carry forward; no action this week. | NFP Tech | mentioned | medium | Sequencing |  | 102
03. Technology | Workday HCM go-live June 29 (HRIS migration, cross-function w/ HR) | In Progress |  |  | Corporate-wide rollout announced 04/14 (src 193); reinforced on Central Region team meeting 04/23 (src 352). Cross-function w/ HR — Roper as downstream consumer, not owner. | Watch for SPI-team enrollment training schedule. | NFP HRIS / Workday team | mentioned | medium | Active |  |  | NEW (not in 4/14 baseline)
03. Technology | Agency Cybersecurity (NY DFS 23 NYCRR 500) annual renewal | In Progress |  |  | Annual compliance filing due 04/15/2026 per Lisa via Idaho/licenses email (src 116). NFP IT delivers underlying controls (Brandon/Tracy stack); Roper owns the filing. | File on dfs.ny.gov compliance portal before 04/15. | Roper / Lisa | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
04. Finance | Workday Company (GL) Creation | Complete | 2026-02-24 16:59:59.999000 | 2026-02-24 16:59:59.999000 | Workday GL company set up at NFP. Baseline marked Done; one stray reference [email#56] confirms Mary Bamford treats GL as in place. No subsequent contradiction. | (close as resolved) | Mary Bamford | implied | medium | Resolved |  | 51
04. Finance | GL Mapping | Complete | 2026-03-03 16:59:59.999000 | 2026-03-03 16:59:59.999000 | Baseline marked Done 4/14. No new evidence in clustering pass contradicts. Carry forward. | (close as resolved) | Mary Bamford | implied | medium | Resolved |  | 52
04. Finance | Closing balance sheet review and upload | Stuck | 2026-03-10 16:59:59.999000 | 2026-03-10 16:59:59.999000 | QB reconciliation undo + closing BS still open after 4/14. Mary Bamford repeatedly chasing same items through 4/24 [email#60][email#133][email#167][email#237][email#291]. Bamford coordinates but does not deliver — Roper is doing the actual fetching from QB/bank. Brooke McKenzie now layered in [email#272][email#276][email#277]. | Undo 2/17 QB reconciliation, then upload closing BS to SharePoint | Roper | implied | high | Ownership Vacuum | 2 | 53 | In Progress → Stuck
04. Finance | Month end and finance & accounting processes onboarding | Stuck | 2026-03-04 08:00:00 | 2026-04-14 16:59:59.999000 | Month-end close drags. March close used estimates per 4/10 transcript [transcript#310]. Bamford repeatedly demands more from Roper rather than absorbing process [email#130][email#137][email#158][email#246]. Disputed on payroll / cost-allocation items [email#134][email#136][email#142][email#143]. | NFP to take ownership of month-end inputs once Workday GL fully populated | Mary Bamford | explicit | high | Ownership Vacuum |  | 54 | In Progress → Stuck
04. Finance | Upload month 1 closing activity | Stuck | 2026-03-25 16:59:59.999000 | 2026-03-25 16:59:59.999000 | Blocked by QB reconciliation undo (baseline row 53). Bamford asking through mid-April [email#159][email#160] but no resolution path landed. | Resolve QB undo, then upload Feb activity | Roper | implied | high | Ownership Vacuum |  | 55 | In Progress → Stuck
04. Finance | Upload month 2 closing activity | Stuck | 2026-04-22 16:59:59.999000 | 2026-04-22 16:59:59.999000 | March close used estimates per 4/10 [transcript#310]; Bamford still chasing March bank statement / source docs through 4/24 [email#130][email#133][email#144][email#294]. NFP cannot close without Roper-fetched docs. | Send March closing activity + bank statement to Bamford | Roper | implied | high | Ownership Vacuum |  | 56
04. Finance | Coupa / Accounts Payable Onboarding | Open | 2026-04-21 16:59:59.999000 | 2026-04-21 16:59:59.999000 | Logan Christianson at NFP genuinely owns the Coupa side [email#156][email#194]. Waiting on technical preconditions (Coupa go-live + supplier list from Roper). Real progress, not stuck. | Roper to share active supplier list with Logan; book working session | Logan Christianson | explicit | high | Sequencing | 7 | 57 | Not Started → Open
04. Finance | Opening balance sheet & working capital true-up calculation | Open | 2026-06-02 16:59:59.999000 | 2026-06-02 16:59:59.999000 | Ryan Mediate at NFP M&A genuinely owns and is moving the WC true-up [email#6][email#21][email#33][email#34][email#35][email#38][email#40]. Bamford cross-referenced [email#88][email#144]. Sequencing on his calculation, not blocked. | Wait on Ryan's working-capital true-up output | Ryan Mediate | explicit | high | Sequencing |  | 58
04. Finance | AmEx statement — 3/20 payment for Mary Bamford | Stuck |  |  | Bamford originally asked 4/6; baseline captured 4/14. She is still re-asking through 4/15+ [email#161][email#167][email#172][email#198][email#200][email#274][email#291] — same ask, never closed. Bamford is demanding from Roper, not delivering — coordinator role mislabeled as ownership. | Send AmEx March statement + supporting docs to Bamford via SharePoint | Roper | explicit | high | Ownership Vacuum | 2 | 59 | Not Started → Stuck
04. Finance | Expense descriptions — Acumen KS $1,250 + OgleTree Deakins $170.10 | Stuck |  |  | 4/6 ask, baseline captured 4/14, Bamford re-asking through 4/24 [email#161][email#172][email#198][email#200]. Now embedded in 4/24 SharePoint demand list (rows 369, 370). Same item; Bamford keeps re-asking. | Provide invoices + classifications for Acumen + OgleTree to Bamford | Roper | explicit | high | Ownership Vacuum | 2 | 60 | Not Started → Stuck
04. Finance | Deposit support — carrier statements for March | Stuck |  |  | 4/6 ask still alive 4/14+ [email#60][email#63][email#79][email#198][email#199][email#274][email#291]. Bamford coordinator role; Roper does the fetching from carrier portals. | Send March carrier statements to Bamford | Roper | explicit | high | Ownership Vacuum | 6 | 61 | Not Started → Stuck
04. Finance | Landmark Bank portal access provisioning for NFP Treasury | Stuck |  |  | 16 emails Mar–Apr coordinated by Rajulla Nadar (NFP Treasury) [email#178][email#182][email#185][email#188][email#190][email#195][email#197][email#201][email#205][email#207][email#208][email#231][email#232][email#233]. Multiple status_signal=Stuck rows. Landmark setup keeps stalling on bank-side workflow. | Escalate to Landmark Treasury Services + loop Crystal as backup admin | Rajulla Nadar | explicit | high | Sequencing |  |  | NEW (not in 4/14 baseline)
04. Finance | Pre-acquisition payroll resolution (Tess & Crystal wages owed — NFP refused, Roper paid wires from Landmark personally) | Disputed |  |  | 9 emails. NFP (Mary Bamford) explicitly refused [email#86]; Ryan Mediate involved [email#69]. Roper personally wired wages from Landmark to clear obligation. NFP pushed liability cost back to seller. | Add to working-capital true-up dispute log; tag for Travis coaching | Roper | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
04. Finance | AmEx card issuance & Concur T&E onboarding (program) | Open |  |  | 5 emails Jackie Searles owns from NFP HR [email#93][email#96][email#97][email#101][email#112]. 4/10 HR ops meeting confirmed Concur+AmEx launched [transcript#334]. Real progress — sequencing on individual card delivery. | Receive AmEx card and confirm Concur access | Jackie Searles | explicit | high | Sequencing |  |  | NEW (not in 4/14 baseline)
04. Finance | Bamford 4/24 SharePoint source-doc demand list — 15 specific transactions by 5/1 | Open |  |  | 15 line-item asks pulled from 4/24 SharePoint screenshots (sources 358–372). Bamford is demanding upload of receipts/invoices for each transaction by 5/1 — coordinator demand pattern, not ownership. Roper must hunt every doc. Includes Chubb personal-premium reclass risk [#371]. | Build single SharePoint upload batch by 5/1 covering all 15 items | Roper | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
04. Finance | Bank balance reporting to NFP Treasury (monthly recurring) | Active |  |  | 3 emails [email#169][email#170][email#171]; Rajulla Nadar requests month-end Landmark balance. Recurring obligation through 6-year SPI shell-life. Roper operating it monthly. | Standing reminder: send Landmark balance to Rajulla on 1st of each month | Roper | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
04. Finance | Add NFP authorized signers to Landmark operating account | Open |  |  | 2 emails [email#47][email#67][email#68]. Rajulla Nadar coordinating signer additions. Real progress; gated on Landmark paperwork. | Submit Landmark signature card with NFP signers | Rajulla Nadar | explicit | high | Sequencing |  |  | NEW (not in 4/14 baseline)
04. Finance | Concur T&E onboarding for Roper specifically | Open |  |  | 1 email [email#155]. Owner unclear — Jackie Searles owns program (milestone C) but Roper-specific access not yet confirmed. | Confirm Concur login + first expense submission | unassigned | unknown | low | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
04. Finance | Agency entity license renewals during 6-year SPI shell-life (46 entity licenses across states; NFP needs them active for rolling BoR + E&O tail but explicitly refused to absorb cost) | Active |  |  | 46 SPI entity licenses must stay active through 6-year tail so NFP can roll Books of Record. Per 4/10 Mary Mullen 1:1 [transcript#310] and 2/27-era pre-acquisition discussion [source#120], NFP refused to absorb renewal cost. Roper pays personally to keep NFP's BoR pathway open. | Build renewal calendar across 46 entities; send invoice schedule to Travis for working-capital dispute log | Roper | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
05. Treasury | Banking Assessment | Complete | 2026-03-03 16:59:59.999000 | 2026-03-03 16:59:59.999000 | Pre-close banking assessment / wire mechanics complete. $25k cap on Landmark legacy account confirmed [src 6, 34]; balance snapshots provided to outside counsel [src 9, 35]; Landmark confirmed as sole business account [src 38]; funds-flow + wire form delivered [src 21]; closing wires initiated and confirmed by NFP Treasury via Aon channels [src 397, 402, 403]. |  | Ryan Mediate | explicit | high | Active |  | 62
05. Treasury | Creation of Wells Fargo Accounts (if needed) | Complete | 2026-03-24 16:59:59.999000 | 2026-03-24 16:59:59.999000 | Not needed per Keara recap (baseline notes_apr14). No new evidence in clustering pass. |  | Keara Rodriguez | implied | medium | Active |  | 63
05. Treasury | Closing selected legacy bank accounts | Open | 2026-03-10 16:59:59.999000 | 2026-03-10 16:59:59.999000 | Per baseline 4/10: one legacy account remains, slated to close as Wells Fargo transition progresses. No clustering evidence advanced this in the reconcile window — workstream stalled while NFP banking platform migration is TBC. | Confirm with NFP Treasury (Rajulla) which legacy account is targeted for closure and the dependency on Wells Fargo / NFP banking migration. | Roper DeGarmo | implied | medium | Ownership Vacuum |  | 64
05. Treasury | Addition of NFP signatory representative on legacy account (if applicable) | Complete | 2026-05-19 16:59:59.999000 | 2026-05-19 16:59:59.999000 | NFP Accounting intros opened the workstream [src 46]; NFP Treasury formally requested adding Caleb Noel + others as signers on Landmark [src 47]; Crystal confirmed three NFP signers added [src 67]; Rajulla acknowledged [src 68]. Signer addition is structurally complete — but see new milestone on portal access (signers without portal = ownership vacuum). |  | Rajulla Nadar | explicit | high | Active |  | 65
05. Treasury | Migration to Wells Fargo / NFP Banking Platform (TBC) | Open | 2026-05-26 16:59:59.999000 | 2026-05-26 16:59:59.999000 | No clustering evidence in reconcile window. Migration to NFP banking platform remains TBC; in the interim Roper continues to operate Landmark on NFP's behalf (see new milestones B and C). | NFP Treasury to confirm migration plan and target date; until then Landmark stays the de facto operating bank. |  |  | low | Ownership Vacuum |  | 66
05. Treasury | Open new SPI business checking at Landmark post-close (Roper + Rachel + Danielle Williams; $50k transferred) | Complete |  |  | Post-close Roper + Rachel opened a separate Landmark business checking with Danielle Williams; Nick Border handled docs; Rachel + Roper provided DLs; Danielle confirmed account opened with $50k transferred [src 175, 179, 180, 191, 192, 203, 204]. Distinct from acquired/legacy account NFP now owns — this is SPI-residual / go-forward. |  | Danielle Williams | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
05. Treasury | NFP Treasury portal access to Landmark for Rajulla/Donna/Jessly | Stuck |  |  | OWNERSHIP VACUUM. Baseline 65 closed (signers added) but NFP Treasury still has no portal access weeks later — Roper is operating the bank for NFP. Rajulla coordinating well; gap is on NFP side. Crystal handed off bank-question routing to Roper post-departure [src 169]; Rajulla repeatedly waiting on Roper for balances [src 170, 176]; Roper himself locked out / questioning why he's still operating the bank [src 178]; Rajulla confirms signers exist but no portal [src 182]; bottleneck illustrated by Roper's travel + password resets [src 183, 185, 188, 190, 195]; Roper escalates asking who go-forward NFP contact is [src 197, 201]; Rajulla defines the three NFP users (Rajulla/Donna/Jessly) [src 205]; Crystal loops Rajulla with Nick Border at Landmark [src 206, 207]; signer-addition wrap [src 208]; Rajulla provides Nick view-only e-statement details [src 231]; Nick sends DocuSign for the three NFP users [src 232, 233]. Rajulla is not the blocker — the access workflow has been crawling for weeks. | Track DocuSign completion for Rajulla/Donna/Jessly view-only e-statement access at Landmark (Nick Border initiated [src 232]); once live, route bank-balance requests off Roper. | Rajulla Nadar | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
05. Treasury | Monthly bank statement + commission delivery to Mary Bamford / NFP accounting | Open |  |  | OWNERSHIP VACUUM. Recurring close cycle Roper still operates as books/cash-source for NFP. February month-end: Mary Bamford asks for outstanding items blocking QBO entries [src 63, 133]; Jenny De Cicco (RubinBrown) confirms interim accounting + asks Roper to undo 2/17 Landmark recon [src 137]; Jenny coordinates with Mary on sale accounting [src 139]; Jenny explicitly questions why NFP is not absorbing the accounting [src 142, 143] (Disputed). March cycle: Roper agrees to send March Landmark statement + un-reconcile [src 145, 159]; sends March statement [src 160]; Mary follows with more requests [src 161]; Roper asks Mary to be specific about doc/QBO needs [src 274] (Stuck). Drive folder access for deposits + commission reports [src 199]; Mary drilling on Progressive [src 362], AIG PCG [src 364], Landmark mobile deposit source docs [src 365]. Cross-cuts integration recap [src 294, 1446] and QBO admin access struggle [src 333]. | Define and document the monthly close packet (statement + commission reports + source docs) with Mary B; tie un-reconcile cleanup to Jenny De Cicco; escalate transfer of accounting ownership to NFP via Mary Mullen recap thread. | Roper DeGarmo | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
05. Treasury | SPI vendor onboarding into Aon Coupa supplier system | Stuck |  |  | Logan Christianson (NFP) launched Coupa setup 3/18 to route SPI vendor expenses through Coupa rather than personal/operating account [src 117]; follow-up 3/24+ remains unanswered — NFP slow on vendor onboarding follow-through [src 156]. | Roper to send Logan the consolidated SPI vendor list + W-9s; Logan to push Coupa team for supplier IDs. | Logan Christianson | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
07. Risk Management | Addition of coverage under NFP/Aon Insurance Program | Complete | 2026-02-17 16:59:59.999000 | 2026-02-17 16:59:59.999000 | Done at close (per Apr 14 baseline). No new evidence in this pass. |  | NFP Corporate Risk Mgmt | inferred | medium | Resolved |  | 67
07. Risk Management | Procurement of ERP's for E&O | Complete | 2026-02-17 16:59:59.999000 | 2026-02-17 16:59:59.999000 | 6-year ERP bound and paid ($15,233 to KAIA). Christopher Sam (NFP Corporate Risk Mgmt) authorized binding [evidence #1361]; Riana Sherwood drove NFP-side tracking and chase [evidence #1197, #1345]; Barb Wise (KAIA) issued endorsement WED4KS006866319 [evidence #1191, #1194]; Roper signed and returned [evidence #1193]. Clean NFP-side coordination — Riana + Christopher Sam executed end-to-end. Counter-example to the dark-variant pattern. |  | Riana Sherwood | explicit | high | Resolved |  | 68
07. Risk Management | Determine agency license retention requirement under E&O retroactive coverage / 6-year ERP | Open |  |  | Roper raised to Lisa whether agency licenses must be maintained given the asset purchase structure + SPI not writing new business + 6-year ERP retroactive E&O coverage [evidence #65]. Cross-function couple with Licensing (08). DARK-VARIANT ADJACENT: Roper is solo-tracking a compliance question that NFP Corporate Risk Mgmt (Christopher Sam) and Licensing should weigh in on — same NFP nodes who executed the ERP cleanly are silent on the downstream compliance implication. | Escalate question to Christopher Sam / NFP Licensing for written guidance before next license renewal cycle. | Roper DeGarmo | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
07. Risk Management | Operational E&O exposure from manual post-close service workflow (no AMS, no service center) | Stuck |  |  | Roper to Caleb: 'just trying to make sure we don't drop any balls that result in E&O' — describes post-close state as 'shut off our agency management system and fired our service center team' on Feb 17 [evidence #275]. Live, ongoing E&O risk-management concern. DARK-VARIANT ADJACENT: Roper alone is naming and tracking the operational E&O exposure; NFP is not coordinating remediation despite owning Risk Mgmt function (cf. Riana/Christopher's clean ERP execution). Roper deferred reassessment to June. | Force NFP-side conversation on AMS/service-center bridge plan; convert Roper's solo concern into a tracked NFP risk item with Christopher Sam. | Roper DeGarmo | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | SIA communication with local contacts | Complete | 2026-02-19 16:59:59.999000 | 2026-02-19 16:59:59.999000 | Closed 2/19. SIA->local NFP handoff completed pre-cluster window. | None — closed. | Sam Brown | explicit | high | Resolved |  | 69
08. Carrier Management | Initial Market Notification to NFP Contacts | Complete | 2026-03-03 16:59:59.999000 | 2026-03-03 16:59:59.999000 | Closed 3/3. Sam Brown circulated initial notice; subsequent threads (s439,s1110) confirm carrier-side acks. | None — closed. | Sam Brown | explicit | high | Resolved |  | 70
08. Carrier Management | Full Market Notification Initiation | In Progress | 2026-04-14 16:59:59.999000 | 2026-04-14 16:59:59.999000 | Owner=Roper per baseline. Active threads w/ Sam Brown + Tess (s122, s124) on carrier-by-carrier coverage; Sue/Susan Clifford team pulled in (s1263) for downstream code-tied dependencies. | Roper to close out remaining named-carrier notifications and confirm with Sam Brown the agency code state per carrier. | Roper | explicit | high | Active | 9 | 71
08. Carrier Management | Ongoing Market Notification and consolidation | In Progress | 2026-04-15 08:00:00 | 2026-05-12 16:59:59.999000 | Heavy live activity (Mar-Apr): Melody Thammavong driving carrier code follow-ups (s545,s887,s888,s1041,s1065,s1066), Bryan Kissinger (s1074,s1096), Mary Mullen (s1047), Roper engaging directly (s250,s895,s1042,s1059,s1069,s1089,s1331). Consolidation tail well past 5/12 finish target. | Owner-of-record: Roper. Push for a single carrier-state matrix (codes-tied, downloads-on, service-center-on, contacts) updated weekly by Melody+Sam Brown. | Roper | explicit | high | Active |  | 72
08. Carrier Management | Berkley One code decision | Not Started | 2026-04-05 00:00:00 |  | Still waiting on Berkley One decision. Brad Millican active on Chubb code in parallel (s1075-s1082,s1092). Kate Conneely engaged on Chubb side (s1118,s1119,s1320). No movement on Berkley One specifically — risk is this slips while attention sits on Chubb/AIG. | Roper to push Brad Millican / Sam Brown for Berkley One code decision; tie to Chubb decision so both close together. | Roper (waiting) | explicit | high | Sequencing | 18 | 88
08. Carrier Management | AIG > PCS One auto downloads live 2/27/26 | Complete |  |  | Tess confirmed (s1219) AIG download path is live as of 2/27/26 — first carrier in the post-acquisition stack to clear codes-tied + downloads-enabled. | None — model template for remaining carriers. Use as proof point for Berkley One/Chubb urgency. | Teresa Wharton | explicit | high | Resolved |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | Chubb agent code decision for Signature book (subcode under 64195 Chicago vs separate) | Open |  |  | Brad Millican leading the decision (s1075,s1077,s1078,s1080,s1082); Roper engaged (s1076); Kate Conneely supporting (s1118,s1119,s1320). Subcode-under-64195-Chicago proposed but not finalized. Codes-tied is precondition for downloads + service center. | Roper push Brad Millican for written code decision this week; copy Sam Brown so the carrier matrix updates immediately on close. | Brad Millican | explicit | high | Sequencing |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | Epic KC1 branch live, carrier downloads NOT enabled (manual processing) | In Progress |  |  | KC1 branch went live 4/17 (s615) but downloads remain off pending codes-tied for each carrier. Concrete restatement of the gap that's tied to baseline rows 71/72 — team running manual processing in the meantime, which compounds the !ALT/Download Suspense pain (see milestone E). | Track each carrier flip from manual->download as codes-tied closes. Nancy Cronin owns Epic side; needs paired carrier list from Sam Brown weekly. | Nancy Cronin | implied | medium | Active |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | PURE/MetLife/Hagerty Epic policy entry rules — download suspense root cause for PURE | Open |  |  | Amy Hill flagged (s1206) PURE/MetLife/Hagerty entry-rule guidance is the root cause of PURE download suspense. Direct precondition for downstream !ALT cleanup (milestone E). | Roper to schedule 30-min w/ Amy Hill + Susan Clifford to lock entry rules per carrier; document in shared SOP. | Amy Hill | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | !ALT / Download Suspense — chronic downstream failure once codes ARE tied | Open |  |  | Susan Clifford owns the suspense queue (s991). Even when codes-tied closes, transactions land in !ALT and need manual triage. AI-agent triage opportunity flagged in cluster decision. | Roper to scope an AI-triage POC with Susan Clifford; near-term, weekly Sue-team report on suspense aging. | Susan Clifford | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | PRC Service Center integration with Epic for PCG Central Region | Open |  |  | Andrea McDonald team handles carrier downloads/processing once service center pickup is live (s1124). Service center integration is the precondition for handoff of routine carrier transactions off Signature staff. | Confirm timeline with Andrea McDonald; identify the 5-10 carriers prioritized for first wave. | Andrea McDonald | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | Aon Edge flood — agency code 1006772 provisioned (private flood quoting) | Complete |  |  | Roper provisioned w/ Aon Edge code 1006772 (s759) — net-new market access via Aon-side affiliation post-acquisition. Quoting capability live. | None — capability live. Push to renewals team so Crystal/team start quoting against it. | Roper | explicit | high | Resolved |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | Universal Property AtlasBridge MFA — carrier access security upgrade | Open |  |  | Tess flagged Universal Property MFA requirement on AtlasBridge (s714). Operational task to maintain access; minor. | Tess to walk team through MFA enrollment this week. | Teresa Wharton | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | NFP cross-carrier signature/document retention policy | Open |  |  | Tess issued compliance directive (s805) for retention across all carriers. Needs translation into Signature workflow + Epic doc-management config. | Map directive to current Signature retention practice; note delta and propose remediation plan to Tess. | Teresa Wharton | explicit | high | Active |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | Chubb/PCG DNR + NY hurricane deductible bulletin distribution | Open |  |  | Mary Mullen routes carrier UW bulletins (s563) — DNRs and NY hurricane deductible updates. Recurring pattern: bulletins arrive Mary->team but distribution to Roper is inconsistent (see milestone K). | Get Roper added to Mary's distribution list for ALL Chubb/PCG bulletins; standing not opt-in. | Mary Mullen | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | AIG Collector Auto Re-Classification — Roper not on distribution list (blind spot) | Open |  |  | Mary fwd'd notice 3/20 (s1026) to Tess only; Roper got it 4/7 (s783) AFTER Tess emailed Mary explicitly (s942/s924) requesting it. Pattern: NFP carrier intel is not routing to Roper proactively. KTF reply (s777) sent same day. AIG is reclassifying 'Exotic' -> 'High Value Collectibles' by value (not age) — rating + youthful operator + conditional renewal exposure across AZ/CO/UT/CA/NV/LA/NM expanding. | Roper to formalize: get added to Central Region carrier-bulletin dist list as standing recipient. Treat each missed bulletin as Ownership Vacuum evidence for the Apr26 diagnostic. | Mary Mullen | explicit | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
08. Carrier Management | BOR/CORG proactive-agent gap — carrier-side signaling not surfacing to receiving agent | Open |  |  | s327 surfaced a BOR/CORG case where carrier-side broker-of-record change did not surface to receiving agent. Same family as milestones J/K: NFP not routing carrier intel proactively. | Bundle with milestone K when raising w/ Mary Mullen / Sam Brown — request standing dist list AND BOR/CORG notification flow. | Unknown (NFP carrier mgmt) | implied | low | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
09. Licensing & Registrations | Agency entity license renewals during 6-year SPI shell-life — NFP needs them active for rolling BoR + E&O tail, refused to absorb administrative burden | Stuck |  |  | WEDGE FINDING / DARK-VARIANT OWNERSHIP VACUUM. NFP requires SPI's 46-state agency entity licenses to remain active for the 6-year shell-life so the rolling Book-of-Record transitions and the E&O tail stay compliant — but Lisa Black explicitly declined NFP responsibility on 03/04/2026 (smoking gun, source id 1205): 'Since this was an asset purchase, NFP will not be handling any of the agency licenses or the agency Cyber security filing. We will be handling the individual licenses.' Roper formally absorbed the burden the next day (id 65, 03/05): 'the agency licenses are on me. If they need to be maintained, I'll bring in an outside firm.' Lisa confirmed (id 66) that state licenses must stay active 'until all the business written under the licenses has officially expired' — i.e., the full 6-year tail. Crystal supplied the inventory on 03/04 (id 1207) and immediately began escalating concrete renewals (Idaho SOS due 03/31, NY Cybersec due 04/15) to Roper (id 116, 03/18), to which Roper replied 'gonna have RubinBrown's small biz department handle some of this kind of thing' (id 118). Roper added 'Review and Renew needed Agency Licenses for SPI LLC' to the master transition task list (id 1204). Reinforcing audio: anka transcript 04/10 (id 334) chunks 8-9 frame the licensing structure NFP refused to absorb; the 02/27 bi-weekly integration review (id 56, transcript 120 chunk 85) is the original meeting where the asset-purchase-vs-license-retention asymmetry surfaced. 7 cluster items support this thesis (ids 65, 66, 116, 118, 1204, 1205, 1207). Roper now owns operational lift NFP requires but refused — must engage compliance counsel and contract a third-party license-administration firm (RubinBrown small-biz division named as candidate). | Engage compliance counsel and select third-party license-administration firm (RubinBrown small-biz division as primary candidate) to handle 46-state agency entity license renewals through the 6-year SPI shell-life. | Roper | Lisa Black explicitly declined NFP responsibility 03/04/2026 (id 1205); Roper formally absorbed 03/05 (id 65) and added to transition master list (id 1204) | high | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
09. Licensing & Registrations | Roper KS Surplus Lines license renewal due 5/1/2026 — unrecognized May renewal sitting in the seam between NFP/RegEd individual scope and agency/state-line scope | Stuck |  |  | OWNERSHIP VACUUM. Kansas Surplus Lines License renewal notice (NPN 4903465) for Roper, due 05/01/2026, was sent to roper.degarmo@nfp.com on 04/15/2026 (source id 644). NFP/RegEd should be catching individual producer renewals per Lisa Black's 03/04 commitment ('We will be handling the individual licenses') and the 04/23 NFP Licensing BI-questionnaire broadcast for May renewals (id 1414) — but the state's notice landed directly in Roper's NFP inbox with no acknowledgment from RegEd, and Roper does not recognize it as his to action. This sits in the seam: Surplus Lines is an individual license (NFP/RegEd scope) but is also a state-line/agency-adjacent credential that may not be in RegEd's standard producer-renewal queue. Risk: lapse on 05/01/2026 if neither side claims it. | Forward 04/15 KS DOI notice (id 644) to NFP Licensing + RegEd; confirm in writing whether KS Surplus Lines is in the May BI-questionnaire scope (id 1414) or requires Roper to file directly. Resolve before 05/01/2026. | Unassigned | Notice landed at roper.degarmo@nfp.com (id 644) without RegEd acknowledgment; NFP/RegEd doesn't claim it, Roper doesn't recognize it as his | low | Ownership Vacuum |  |  | NEW (not in 4/14 baseline)
09. Licensing & Registrations | Individual producer license renewals via NFP/RegEd — May Background Information (BI) questionnaire workflow | Active |  |  | ACTIVE / WORKING COUNTER-EXAMPLE. NFP Licensing 04/23 broadcast (id 1414) instructs producers with May renewals to complete the BI questionnaire so RegEd can submit applications and fees to state DOIs. Confirms RegEd is operationally handling individual producer renewals as Lisa Black committed on 03/04 (id 1205, id 1208). Supporting workstream: Jasper Oliver (RegEd Licensing Success Analyst) collected Roper's employment history for producer profile setup on 03/17 (ids 1058, 1060). Tess Presnal MA P&C licensing path coordinated by Brad Millican / RegEd (id 115). NPN exchange for Berkley One/Chubb access setup completed (ids 1078, 1080). This is the functional half of the licensing function — used as the structural counter-example to the agency-license wedge: individual = NFP/RegEd owns; agency = Roper owns alone. | Complete May BI questionnaire per NFP Licensing 04/23 broadcast; verify KS Surplus Lines (Milestone B) is included in scope. | Lisa Black + RegEd | Lisa Black committed NFP/RegEd ownership of individual licenses 03/04 (ids 1205, 1208); RegEd executing via Jasper Oliver onboarding (ids 1058, 1060) and 04/23 BI broadcast (id 1414) | high | Active |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | Regional Sales Updates — Central Region (Mary Mullen) | Active | 2026-04-22 08:00:00 | 2026-05-19 16:59:59.999000 | Mary Mullen (96 mentions) anchors Central Region cadence. 99 linked items including biweekly Central Region Leader Calls and KTF threads. Brett Woodward (12 mentions) coordinates regionally. | Continue bi-weekly Central Region cadence; surface Roper-specific asks separately | Mary Mullen | explicit | high | Active |  | 76
10. Region/Sales/Ops | Integration — Send ranked list to Keara Connelly | In Progress | 2026-04-05 00:00:00 |  | Keara Connelly is integration PM. 37 linked items spanning Integration Review cadence and Roper deliverables. | Send ranked priority list to Keara | Roper | explicit | high | Sequencing | 1 | 80
10. Region/Sales/Ops | Tess full-time conversation with Brett Woodward | Not Started | 2026-04-05 00:00:00 |  | Roper-owned conversation pending with Brett Woodward. | Schedule conversation with Brett re Tess full-time role | Roper | explicit | high | Sequencing | 3 | 81
10. Region/Sales/Ops | Goals in UltiPro | Not Started | 2026-04-05 00:00:00 |  | HR system entry — 10/20/30 SMART goal drafted per UltiPro topic file. | Enter goals in UltiPro | Roper | explicit | high | Active | 12 | 84
10. Region/Sales/Ops | NB premium goal for EPIC | Not Started | 2026-04-05 00:00:00 |  | Awaiting clarity from Mary on EPIC NB goal format. | Clarify what Mary Mullen needs, provide NB premium goal | Roper | explicit | high | Active | 13 | 85
10. Region/Sales/Ops | Life insurance policy list + commission | Waiting | 2026-04-05 00:00:00 |  | Roper waiting on internal life data before delivery. | Provide active life policy list | Roper | explicit | high | Active | 17 | 87 | Not Started → Waiting
10. Region/Sales/Ops | P&C Town Hall — April 20 | Complete | 2026-04-05 00:00:00 |  | Town Hall date Apr 20 — past as of 4/26 reconcile. | None — past event | Roper | explicit | high | Resolved | 19 | 90 | Not Started → Complete
10. Region/Sales/Ops | Susan Clifford — ALT report / AI agent | Stuck |  |  | Susan Clifford waiting on sample data to advance ALT monthly rollup AI agent. | Send sample data to Susan Clifford | Susan Clifford | explicit | high | Ownership Vacuum |  | 94 | Waiting → Stuck
10. Region/Sales/Ops | NFP Personal Risk Summit — Terranea Apr 13-16 | Complete |  |  | Summit collapsed from 52 cluster items; mostly contextual/calendar entries. Discrete follow-ups tracked independently below. | Capture follow-ups (TGV, Gil Lai, AI evangelism) as separate milestones | Roper | explicit | high | Resolved |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | TGV insurance whitepaper — Brett Woodward collaboration | Open |  |  | Brett brought Roper into Isabel Sjodin's whitepaper effort; intro call Apr 13. 8 linked threads. | Wait for Isabel Sjodin (Timber Grove VC) draft; respond when received | Brett Woodward | explicit | medium | Sequencing |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | Goldman Ayco lead — Swans / celebrity renter (Jeff DeMaio crossover) | Open |  |  | Active April 21-22 thread. Jeff DeMaio bridge from Goldman Ayco into NFP after 2026-02-17 acquisition. 7 linked items. | Advance Swans + celebrity renter intro through Jeff DeMaio (now NFP via GS Ayco acquisition) | Roper | explicit | high | Sequencing |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | AIG Collector Auto Re-Classification — Roper not on dist list (cross-ref to Carrier Mgmt) | Open |  |  | Distribution list gap — Roper missed AIG Collector Auto re-class memo. Primary milestone lives in Carrier Mgmt; this is a Region/Sales cross-reference. 5 items. | Confirm Roper added to AIG distribution list; primary tracking is in Carrier Mgmt function | Tess Presnal | mentioned | medium | Active |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | Press Release & Client Communication — acquisition announcement (cross-ref Marketing row 22) | Complete |  |  | Acquisition press/client comm completed. Cross-reference only; primary in Marketing function. 4 items. | None — primary tracked in Marketing row 22 | Roper | explicit | medium | Resolved |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | AI evangelism with NFP leadership (Mark Rieder, Katherine Minami) | Open |  |  | Roper-driven sales/strategy. Mark Rieder (NFP CHRO) + Katherine Minami engagement. Per diagnostic lens: note but don't over-elevate. 4 items. | Continue AI memo/synopsis cadence with Rieder + Minami; Roper-driven strategy item | Roper | explicit | high | Sequencing |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | Gil Lai NY intro list — Beyer/Bancker pipeline | Open |  |  | Roper-driven sales pipeline via Gil Lai. Michael Beyer/Bancker is large untapped commercial. Note but don't over-elevate per diagnostic lens. 4 items. | Advance Michael Beyer (Bancker) intro — #1 on Gil Lai's NY list | Roper | explicit | high | Sequencing |  |  | NEW (not in 4/14 baseline)
10. Region/Sales/Ops | Day in the Life Reviews — NFP shadowing Signature workflows | Open |  |  | NFP shadowing Signature workflows — Mar 27 session accepted. 3 items. | Continue Day-in-Life sessions; coordinate with Mary Mullen | Roper | explicit | medium | Sequencing |  |  | NEW (not in 4/14 baseline)

## Comments & Changelog
Changelog: 2026-04-14 baseline → 2026-04-26 refresh
Generated: 2026-04-26T17:02:47
Summary
Total milestones: 138
New milestones (not in baseline): 46
Status changed since baseline: 18
Problem Type distribution
Active | 42
Sequencing | 37
Resolved | 34
Ownership Vacuum | 25
Owner distribution (top 15)
Roper | 33
unassigned | 12
NFP Tech | 11
Mary Mullen | 6
Jackie Searles | 5
Susan Clifford | 4
NFP Marketing | 4
Rajulla Nadar | 4
Roper DeGarmo | 4
NFP HR (corporate) | 3
Andria Griffin | 3
Mary Bamford | 3
Teresa Wharton | 3
Nancy Cronin | 2
Kim Pillar | 2

## Function Summary
Function | Total | Ownership Vacuum | Sequencing | Resolved | Active | New (not in baseline)
01. HR | 24 | 2 | 1 | 19 | 2 | 5
02. Marketing | 19 | 0 | 12 | 4 | 3 | 2
03. Technology | 27 | 0 | 10 | 0 | 17 | 2
04. Finance | 19 | 11 | 5 | 2 | 1 | 8
05. Treasury | 9 | 4 | 0 | 0 | 5 | 4
07. Risk Management | 4 | 2 | 0 | 2 | 0 | 2
08. Carrier Management | 17 | 3 | 2 | 4 | 8 | 12
09. Licensing & Registrations | 3 | 2 | 0 | 0 | 1 | 3
10. Region/Sales/Ops | 16 | 1 | 7 | 3 | 5 | 8